Project Plan

Automated Regression Engine + UI for Brand × Channel Volume Sales Modeling

Big Chalk Analytics × Northwestern MSDS Capstone — Summer 2026

Team: Feifan Liu · Boqi Niu · Jiahao Li      Faculty: Abid Ali      Sponsor contact: Alex Hathcock      July 14, 2026

# 1. Project Overview

Big Chalk Analytics, a marketing-analytics consultancy based in Evanston, IL, supports a national CPG manufacturer that sells many niche products across up to nine retailer channels. Modeling volume sales for every brand and channel by hand does not scale. Our capstone project builds an automated regression engine that constructs a volume-sales model for every Brand × Retailer-Channel combination — with predictors spanning trade, distribution, price, media (adstocked), competition, macroeconomics, and seasonality — and wraps it in a dashboard that lets a non-technical analyst upload data, run all models, inspect diagnostics and contribution (“due-to”) reports, and manually override variable selection and coefficient bounds before finalizing.

The dataset is three years (Jan 2023 – Dec 2025, 156 weeks) of weekly data for 10 anonymized brands across up to 9 channels, roughly 113 columns per brand, at a Channel × Brand × Week grain.

## 1.1 Objectives and success criteria

- Automatically build a defensible regression model for every Brand × Channel slice (82 combinations in the pilot dataset), with sign- and bound-constrained coefficients, VIF screening, and time-based holdout validation.

- Support analyst overrides: force or exclude variables, set coefficient bounds, and re-run — the “client-mandated variable” workflow the sponsor requires.

- Report coefficients, fit metrics, t-stats, VIF, and yearly contribution decompositions (due-tos) per model.

- Deliver a dashboard covering data upload → model design → batch run → drill-down → manual re-run, usable on a new client datafile without code changes.

- Quality bar: batch completes in minutes, models achieve reasonable fit (median R² ≈ 0.9 and median holdout MAPE ≈ 10% on the pilot data), and every methodological choice is documented and defensible to the sponsor.

# 2. Scope

## 2.1 In scope

- Data ingestion and validation for Excel workbooks at the Channel × Brand × Week grain, with product sheets and modeling targets auto-detected.

- Feature engineering per the sponsor's conventions: normalized adstock transforms with per-media decay rates, config-table variable mapping (family, expected sign, bounds, role: auto / force / exclude).

- Automated model selection (forward stepwise with VIF pruning) and bounded least-squares estimation; configurable target and modeling window (104-week set-year with tail holdout).

- Batch execution across all Brand × Channel combinations with a consolidated summary and failure flags.

- Dash-based UI: run & diagnostics, per-variable controls, contribution reporting, and batch overview with drill-down.

- Course deliverables: project plan, testing plan, EDA report, design document, status reports, final report and presentation.

## 2.2 Out of scope

- Production deployment and hosting at Big Chalk (packaging guidance will be documented; hosting decisions rest with the sponsor).

- Non-regression model families (e.g., ML forecasters) as the final deliverable — the sponsor requires interpretable, constraint-capable regression.

- Data acquisition or cleaning beyond the anonymized files provided by the sponsor.

- Event-overlay modeling for unrecorded market shocks (flagged as a possible extension, pending sponsor input).

# 3. Team, Roles, and Responsibilities

The team operates on a shared-ownership model: all three members co-own each phase and its deliverables, with the lead role rotating so that every member drives at least one major phase and one written deliverable. This keeps knowledge distributed and removes single points of failure on a three-person team.

| Role | Responsibilities | Assigned to |
| --- | --- | --- |
| Phase lead (rotating) | Drives the active phase: sets weekly goals, integrates work, owns the phase deliverable draft | Rotates — Feifan Liu, Boqi Niu, Jiahao Li |
| Engineering & code review | Pipeline and UI code quality; every merge reviewed by a second member | Shared (all) |
| Modeling & validation | Method choices, diagnostics, holdout validation, sponsor methodology alignment | Shared (all) |
| Documentation & findings | Living findings document, README, course deliverables | Shared (all) |
| Sponsor & faculty liaison | Meeting agendas, minutes, follow-ups from the Monday sponsor sync | Rotates with phase lead |

## 3.1 Communication and tracking

- Sponsor sync: weekly, Mondays 11:00–12:00 with Alex Hathcock (Big Chalk). Agenda circulated beforehand; decisions logged in the findings document.

- Team working sessions: at least twice weekly, plus ad-hoc pairing on blocking issues.

- Faculty check-ins: per course schedule with Prof. Abid Ali; status reports submitted as required by each module.

- Tracking: private GitHub repository (code, issues, commit history), a living Findings.md methodology log updated after every sponsor review, and per-phase output artifacts (model summaries, charts) checked into the project folder.

# 4. Timeline and Milestones

The project runs June 22 – August 25, 2026. Phases 1–3 are complete and validated with the sponsor; Phase 4 is underway. Remaining effort concentrates on UI refinement, testing, and final reporting.

| Phase | Window | Status | Milestone / exit criteria |
| --- | --- | --- | --- |
| 1. Data understanding | Jun 22 – Jun 28 | Complete | Grain, column families, and target decompositions documented; leakage columns identified and excluded |
| 2. Single-model engine | Jun 29 – Jul 5 | Complete | Automated pipeline reproduces sponsor's production approach on Brand 1 × Channel 1 (coefficient agreement to 3e-07); sponsor review Jul 6 incorporated |
| 3. Scale to all combinations | Jul 6 – Jul 12 | Complete | 80 of 82 slices modeled (2 correctly skipped); median R² 0.89, median holdout MAPE ≈10%; full batch ≈9 s |
| 4. UI / dashboard | Jul 6 – Aug 2 | In progress | Four-tab Dash app functional (run & diagnostics, variable controls, contributions, batch overview); remaining: per-slice config overrides, usability polish, sponsor feedback round |
| 5. Testing & hardening | Jul 13 – Aug 16 | Starting | Testing plan executed: unit, integration, system, and UAT (with sponsor/peer team); defects triaged and resolved |
| 6. Final report & presentation | Aug 10 – Aug 25 | Not started | Final report drafted, reviewed, and submitted; presentation rehearsed; final presentation Tue Aug 25, 10:00 AM |

## 4.1 Course deliverable schedule

| Deliverable | Due | Points | Owner |
| --- | --- | --- | --- |
| Module 3: Project Plan (this document) | Wed Jul 15, 2026 | 75 | Team (shared) |
| Module 3: Testing Plan | Sun Jul 19, 2026 | 75 | Team (shared) |
| Module 4: Data Analysis Report (EDA) | Sun Jul 19, 2026 | 100 | Team (shared) |
| Module 4: Design Document | Sun Jul 19, 2026 | 150 | Team (shared) |
| Status reports / test reports | Per module schedule | — | Phase lead |
| Final presentation | Tue Aug 25, 2026, 10 AM | — | Team (shared) |

# 5. Current Status

The project is ahead of the suggested phasing. The engine and batch layer are complete and sponsor-validated: 80 Brand × Channel models build in about nine seconds with median R² of 0.89 and median holdout MAPE near 10%. The July 6 sponsor review reshaped five areas — adstock normalization, config-driven variable mapping, configurable targets, the set-year modeling window, and contribution reporting — all implemented and re-validated. The dashboard already loads arbitrary client datafiles and batch-runs every combination from the browser. A case study (Brand 1 × Channel 1, where forcing a distribution variable cut holdout error from 73% to 32%) demonstrated the analyst-override workflow end to end.

# 6. Risks and Issues

Risks are reviewed at each Monday sponsor sync; issues are tracked in the repository and in the findings log.

| Risk / issue | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Structural changes not present in the data (e.g., suspected Brand 1 late-2025 delisting) cap achievable accuracy on some slices | High | Medium | 8 high-MAPE slices flagged to sponsor; force-variable workflow mitigates; event-dummy mechanism scoped as extension if sponsor confirms events |
| Sponsor availability limited to weekly syncs; open policy questions (trade coefficient bounds, adstock decay priors) could stall decisions | Medium | Medium | Batch open questions for Monday syncs; proceed with documented industry-standard defaults that are config-swappable |
| New client datafiles deviate from expected layout (naming quirks already observed, e.g., Brand 2's renamed media columns) | Medium | Medium | Config-table design absorbs naming changes without code edits; validated against a synthetic alien-format workbook; ingestion tests in the testing plan |
| Residual autocorrelation (low Durbin–Watson) on several slices may understate coefficient uncertainty | Medium | Low | Raised with sponsor; HAC standard errors or lagged terms scoped as Phase 4+ enhancement if required for due-to work |
| Deployment environment at Big Chalk undecided, affecting packaging | Medium | Low | Keep the app dependency-light and environment-agnostic; document setup; decision requested from sponsor |
| Team schedule compression in August (testing overlaps final reporting) | Medium | Medium | Testing begins mid-July, well before the final-report window; shared ownership lets any member absorb slack |

# 7. Assumptions and Dependencies

- The anonymized dataset provided by Big Chalk is representative of the client data the tool will ultimately serve.

- Volume Sales remains the primary modeling target (per sponsor preference); the pipeline nonetheless supports configurable targets.

- Sponsor methodology conventions (normalized adstock, per-media decays, set-year window) remain stable for the project duration; changes are absorbed via configuration.

- UAT participation from the sponsor and/or the peer capstone team is available in August, per the course's testing-plan guidance.